## TRAIN MATRIX
[19 empty] | Train Matrix | [19 empty] | (Matrix Template Rev 2)
[19 empty] | WEEK Nr. & DATES: |  |  | Week 1 Easter 2021 01/04/21 - 06/04/21 | MATRIX OWNER: | Jacob Dixon |  |  |  | CONTACT NUMBER: |  |  | 07702967887
[19 empty] | JOB Nr. & LOCATION: |  |  | JNP0280 Oakwood P&C Re-Ballast | SCOPE: | P&C Re-Ballast 140m (9ab Pts, 55Rd and Diamond) | [10 empty] | Trains |  | 6
[19 empty] | THIS TRAIN PLAN IS BASED ON: |  |  | Transplant[ SPOIL - 7.5m per GP & 6.5m per TU based on 230mm excavation, SAND, 23m per TU, B.BALLAST - 10m per GP & 10.5m per TU, SLEEPERS - 105 or 84No Concrete/ 64 nos Timbers per GP, T.BALLAST 18m per wagon.] GBRf[ SPOIL - 17m per Falcon, SAND 65m per Falcon, BALLAST, 25m per Falcon or SideTipper, TOP BALLAST 45m per AutoBallaster and, 45m per Falcon]
TOTALS |  | Priority | ENTRY HEADCODE / TRAIN Nr. | VEHICLES | [16 empty] | WEST / NORTH | TRAIN CONFIGURATION & ORIENTATION | EAST / SOUTH | LOADING DETAILS | [7 empty] | RESULTING SITE PROGRESS DETAILS (m) | [5 empty] | WORK TIMES | REQUESTED TIME |  | EXIT HEAD CODE | STACK Nr.
GP | TU |  |  | Length (m) | Cl 66 | (1) NTC | (13) SL | (5) AB | (5/8) ST | FA | SA | TE | Batt Loco | Schö Loco | Tamp | HD | HW | RW | GP | TU | Enter Poss'n Limit Here | GBRf - orientation AT WORKSITE TRANSPLANT - orientation leaving RUISLIP | Enter Poss'n Limit Here | SPOIL GP TU FA | SAND GP TU FA | B. BAL GP TU FA |  |  | SLPRS SA GP | T. BAL. FA AB TP |  | RAIL OUT | SLPR OUT | Spoil | B.Ballast | Sleepers | T. Ballast | PROVISIONAL | Time At Protecting Signal-ENTERING | Time at Signal - EXITING
6 | 0 | 1 | 540 | 131.9 | [8 empty] | 2 | [5 empty] | 6 |  | Wood Green | Loco, 2no GP (materials, 15T Chippings in Tonne bags) 5no GP's (Loose Ballast) ,Loco | Cockfosters |  |  | 4 | [8 empty] | 32 |  |  | Friday 07:00 - Saturday 07:00 | Thursday Night | Saturday Late Current | 540 | 1
8 | 6 | 1 | 541 | 132.58 | [8 empty] | 2 | [5 empty] | 2 | 6 | Wood Green | Loco,2no GP (Empty) ,6no TUs (loose ballast) , Loco | Cockfosters |  |  |  | 6 |  |  |  |  | 0 |  |  | 95 | 0 |  | Saturday 06:00 - Sunday 09:00 | Thursday Night | Monday Late Current | 541 | 1
14 | 6 | 1 | 542 | 131.9 | [8 empty] | 2 | [5 empty] | 6 |  | Wood Green | Loco, 6no GPs (loose Ballast),Loco | Cockfosters |  |  | 6 | [8 empty] | 143 | 0 |  | Sunday 11:00 - Monday 09:30 | Thursday Night | Monday Late Current | 542 | 1
19 | 6 | 1 | 543 | 115.57 | [8 empty] | 2 | [5 empty] | 5 |  | Wood Green | Loco, 5no GPs (loose Ballast),Loco | Cockfosters |  |  | 5 | [8 empty] | 183 | 0 | 0 | Monday 03:00 - Monday 22:00 | Thursday Night | Monday Late Current | 543 | 1
24 | 6 | 1 | 544 | 115.57 | [8 empty] | 2 | [5 empty] | 5 |  | Wood Green | Loco, 5no GPs (loose Ballast),Loco | Cockfosters |  |  | 5 | [8 empty] | 223 | 0 |  | Monday 10:00 - Monday 22:00 | Thursday Night | Monday Late Current | 544 | 1
30 | 6 | 2 | 545 | 131.9 | [8 empty] | 2 | [5 empty] | 6 |  | Wood Green | Loco, 3no GPs (Empty for scrap), 3no GPs (Ballast) ,Loco | Cockfosters |  |  | 3 | [8 empty] | 247 |  |  | Monday 12:00 - 23:00 | Friday night late current | Monday Late current | 545 | 2
|  |  |  | TOTALS: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 30 | 6
TRANSPLANT ENGINEERING TRAINS
TRAINS RUNNING TO THE POSSESSION:
Thursday night |  |  |  |  | Trains will be pathed out of Ruislip depot as per publications and travel to the east end Piccadilly line. Trains will stable as follows and possession will be taken around them : WT540 - Bounds Green Platform 1 WT541 - Arnos Grove Plaform 1 WT542 - Southgate Platform 1 WT543 - Cockfosters Platform 1 (shorter length to fit in platform) WT544 - Cockfosters Platform 4 (shorter length to fit in platform)
Friday night |  |  |  |  | WT545 will travel to the possession in late current and enter the possession at the Western limits before travelling East to be moved into position by the train SPC
RUNNING TRAINS WITHIN POSSESSION:
Throughout |  |  |  |  | Once possession is taken WT543 & WT544 remain in Cockfosters platforms until required. WT540 - WT542 will travel east and cross 8pts West of Oakwood onto the WB road, Trains will then travel east and stable 500m east of Oakwood Station. RRV's will on-track within Cockfosters Depot and travel to site as per the send and recieve plan, once on site they be worked as per staging diagrams. All trains will be worked as per the Staging diagrams and once worked they will all cross onto the WB road using points within the worksite. Trains will then travel west ready to exit at the western possession limits. All trains exiting will be handed over to the Train SPC at Arnos Grove (drainage works) and they will manage the exit process of the trains, Drainage also have to option to fill up any trains as they pass through. WT545 that enters the possession will enter on the EB road and travel through the drainage worksite, they will travel to Oakwood platform where they will stop and wait until ready to work. The train SPC will manage arriving trains and liaise with lead SPC and Site Manager as to when they are required on site. Rusty Rail moves: WT545 will be utilised as required for Rusty rail moves.
RUNNING TRAINS FROM THE POSSESSION
Saturday night |  |  |  |  | WT540 will exit the possession in late current from the Possession limts at Bounds Green and travel back to Ruislip in Late Current.
Monday night |  |  |  |  | WT541 - 545 will exit the possession in late current from the Possession limts at Bounds Green and travel back to Ruislip in Late Current.
TAMPING ARRANGEMENTS
Sunday Day |  |  |  |  | Not required
TRACTION CURRENT ARRANGEMENTS FOR MOVEMENT OF ENGINEERS TRAINS
Thursday Night Friday Night Saturday night Monday night |  |  |  |  | Stack 1 trains will travel to the possession as per publications, late current required for trains to travel to possession. Late current is required on Friday night from Ruislip to the possession until the passage of WT545. Late current is required on Saturday night from the Possession to Ruislip Depot for the passage of WT540. Late current is required on Monday night from the possession to Ruislip Depot for the remaining trains on site WT541 -WT545
REVISION HISTORY |  |  |  |  | DETAIL OF CHANGES | [29 empty] | AUTHOR |  |  |  |  | DATE
Draft | [34 empty] | J Dixon |  |  |  |  | 2021-01-26
Revison 1 | [34 empty] | J Dixon |  |  |  |  | 2021-03-04
Revision 2 |  |  |  |  | Amendments to WT540 consist, changes to WT541 exit route (now Monday late current) due to line controller issues. Amendments to shift working times and reduction in GP wagons therefore consist changes. | [29 empty] | J Dixon |  |  |  |  | 2021-03-24
DO NOT PRINT THE CELLS BELOW THIS LINE. | [20 empty] | DO NOT PRINT THE CELLS BELOW THIS LINE. |  | DO NOT PRINT THE CELLS BELOW THIS LINE. | [9 empty] | DO NOT PRINT THE CELLS BELOW THIS LINE. | [8 empty] | DO NOT PRINT THE CELLS BELOW THIS LINE.
Distribution: Distribute to [Transplant - Steve.Howley@tubelines.com] [GBRf - Malcolm.Trotter@GBRailfreight.com Richard.Biddle@GBRailfreight.com Andrew.Whitehead@GBRailfreight.com] [PossessionPlanners@tfl.gov.uk] [ARA Distribution will be via Possession Planner] Clive Maxwell [Ruislip Train Loading Bay - Mark.Cain@BBRail.com William.Lupson@BBRail.com Patrick.Hogan@BBRail.com] [responsible TP Project Manager, Delivery Manager and Construction Manager] [Matrix Owner and Parties owning trains shown on the Matrix]
Changes to be highlighted in red text. Only highlight the actual changes and not the entire field. Hide cells if there is only one fleet in use on the possession. On multiple work scopes, use cell shading to highlight allocation of trains. Recycled Transplant Trains - show the original train number in brackets alongside the new train number in order to track stock recycling eg 741 (641) shows that train 741 uses the vehicles from train 641. Transplant train use number 5xx, 6xx and 7xx. The digits '8' & '9' cannot be used. FILE NAME to be in the following format: Job Number, Week Number, Location, “Train Matrix”, Rev Nr, Date eg MF1.1 (Wk53) HOTH Train Matrix Rev 2 6-7-12

## Acknowlegement Form
Train Matrix - Acknowledgement and review record
| WEEK Nr. & DATE: | Week 1 Easter 2021 01/04/21 - 06/04/21 | REVISION Nr.: | 0 | MATRIX OWNER: | Jacob Dixon
| JOB Nr. & LOCATION: | #REF! | SCOPE: | #REF!
| JOB Nr. & LOCATION: | 0 | SCOPE: | 0
I acknowledge receipt of the Train Matrix for Week Week 1 Easter 2021 01/04/21 - 06/04/21 revision 0 and confirm that the arrangements are acceptable in principle, and can be resourced subject to the following comments:
Name: | Signature: |  | Organisation: |  |  |  | Date:
Comment 1
Comment 2
Comment 3
Comment 4
Comment 5
Comment 6
Comment 7
Comment 8