## DEFECTS
Defect Id | Date Inspected | Road Id | Road Name | Location | Description | Status | Priority Code | Activity Type | Defect Type | Action Type | Due Date | Priority
797863 | 2019-06-04 22:47 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | WB TELFORD RD AT EXIT FROM BP GARAGE ADJ TO ATM 50 MTRS AFTER JW BOUNDS GREEN RD | CRACKED TACTILES+ SUNK KERB | COMPLETED | 2H | Footways And Cycle Tracks | Slab cracking | Permanent | 2019-06-11 22:47 | 7 Day Defect
798324 | 2019-06-07 00:41 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | PINKHAM WAY EB J/W BOUNDS GREEN RD BY END OF TUNNEL | MISSING IGP | INSTRUCTED | 1 | Safety Bollards: Face/Structure/Fixings | Missing | Permanent | 2019-07-05 00:41 | Priority 1
798324 | 2019-06-07 00:41 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | PINKHAM WAY EB J/W BOUNDS GREEN RD BY END OF TUNNEL | MISSING IGP | INSTRUCTED | 1 | Safety Bollards: Face/Structure/Fixings | Missing | Temporary | 2019-06-08 00:41 | Priority 1
798334 | 2019-06-07 01:17 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | WB C/W A406 TELFORD RD JW HASTINGS ROAD | GRAVEL SPILLAGE IN C/W | INSTRUCTED | 1 | Sweeping And Cleansing | Debris in traffic lane | Permanent | 2019-06-08 01:17 | Priority 1
798335 | 2019-06-07 01:33 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | TELFORD RD J/W BOUNDS GREEN RD LEFT SIDE OF YELLOW BOX JUNCTION | FAILED PATCH BITMAC | INSTRUCTED | 1 | Minor Carriageway Repairs | Patch - loss of material | Permanent | 2019-07-05 01:33 | Priority 1
798335 | 2019-06-07 01:33 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | TELFORD RD J/W BOUNDS GREEN RD LEFT SIDE OF YELLOW BOX JUNCTION | FAILED PATCH BITMAC | INSTRUCTED | 1 | Minor Carriageway Repairs | Patch - loss of material | Temporary | 2019-06-08 01:33 | Priority 1
801445 | 2019-06-29 02:48 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | A406 TELFORD RD EB NB BTW OPP JUNCTION HASTINGS RD AND BEXHILL RD | LARGE TREE BRANCH FALLEN INTO F/W | COMPLETED | 1E | Hedges And Trees: General | Other | Permanent | 2019-07-27 02:48 | Priority 1 (ECO
801893 | 2019-07-02 16:49 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | TELFORD RD EB OPP J.O BEXHILL RD | CRACKING AROUND GULLY | COMPLETED | 2M | Covers,Gratings,Frames,Boxes | Cracking around ironwork | Permanent | 2019-07-30 16:49 | 28 Day Defect
803556 | 2019-07-16 09:28 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | Telford rd jw station rd on CI at XING point | Missing PGR | INSTRUCTED | 1 | Boundary Fences: Metal/Concrete | Missing | Permanent | 2019-08-13 09:28 | Priority 1
803556 | 2019-07-16 09:28 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | Telford rd jw station rd on CI at XING point | Missing PGR | INSTRUCTED | 1 | Boundary Fences: Metal/Concrete | Missing | Temporary | 2019-07-17 09:28 | Priority 1
809906 | 2019-08-30 13:51 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | bowes rd jw wilmer way | damaged pgr | COMPLETED | 1 | Safety Fences: Metal/Concrete | Damaged/deformed | Permanent | 2019-09-27 13:51 | Priority 1
809906 | 2019-08-30 13:51 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | bowes rd jw wilmer way | damaged pgr | COMPLETED | 1 | Safety Fences: Metal/Concrete | Damaged/deformed | Temporary | 2019-08-31 13:51 | Priority 1
817962 | 2019-11-01 01:26 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | A406 J/W BOUNDS GREEN RD | CAR HAS HIT PGR | COMPLETED | 1E | Safety Fences: Metal/Concrete | Accident damage | Permanent | 2019-11-29 01:26 | Priority 1 (ECO
817962 | 2019-11-01 01:26 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | A406 J/W BOUNDS GREEN RD | CAR HAS HIT PGR | COMPLETED | 1E | Safety Fences: Metal/Concrete | Accident damage | Temporary | 2019-11-02 01:26 | Priority 1 (ECO
820226 | 2019-11-05 19:45 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | TELFORD RD WB OS BP GARAGE 50 MTRS B4 PINKHAMWAY BRIDGE | FAILED PATCH IN CW | SELECTED | 2M | Minor Carriageway Repairs | Failed patch : loss of material | Permanent | 2019-12-03 19:45 | 28 Day Defect
823245 | 2019-12-03 20:29 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | TELFORD RD EB JW STATION RD ON CI OPP JO BOUNDSGREEN LN | MISSING PGR | COMPLETED | 2H | Street Furniture | Missing | Permanent | 2019-12-10 20:29 | 7 Day Defect
827107 | 2020-01-07 12:21 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | TELFORD RD WB OS 45 30 MTRS B4 JW BEXHILL RD | FAILED PATCH IN CW | SELECTED | 2M | Minor Carriageway Repairs | Failed patch : loss of material | Permanent | 2020-02-04 12:21 | 28 Day Defect
831820 | 2020-02-04 11:58 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | A406 TELFORD RD WB JUST AFTER JW LOWERMAIDSTONE RD OS 119 | FAILED PATCH AROUND GULLY | COMPLETED | 2M | Covers,Gratings,Frames,Boxes | Cracking around ironwork | Permanent | 2020-03-03 11:58 | 28 Day Defect
831821 | 2020-02-04 11:58 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | TELFORD RD EB OPP 59 40 MTRS B4 JO BEXHILL RD LN 1 | FAILED PATCH AROUND BLOCKEDBGULLY | COMPLETED | 2M | Covers,Gratings,Frames,Boxes | Cracking around ironwork | Permanent | 2020-03-03 11:58 | 28 Day Defect
832470 | 2020-02-07 01:26 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | LOWER MAIDSTONE RD J/W TELFORD RD OPP 3 | LEANING SIGN AND POST R/R/ SIGN | INSTRUCTED | 1A | Signs: Face/Structure/Fixings | Damaged | Permanent | 2020-03-06 01:26 | EMG - 24hr Defe
832470 | 2020-02-07 01:26 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | LOWER MAIDSTONE RD J/W TELFORD RD OPP 3 | LEANING SIGN AND POST R/R/ SIGN | INSTRUCTED | 1A | Signs: Face/Structure/Fixings | Damaged | Temporary | 2020-02-08 01:26 | EMG - 24hr Defe
832474 | 2020-02-07 02:15 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | TELFORD RD WB OPP J/X BEXHILL RD | SIGN POST DOOR OFF | INSTRUCTED | 1A | Post Defect | Damaged/Deformed | Permanent | 2020-03-06 02:15 | EMG - 24hr Defe
832474 | 2020-02-07 02:15 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | TELFORD RD WB OPP J/X BEXHILL RD | SIGN POST DOOR OFF | INSTRUCTED | 1A | Post Defect | Damaged/Deformed | Temporary | 2020-02-08 02:15 | EMG - 24hr Defe
836287 | 2020-03-03 21:31 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | TELFORD RD EB JUST B4 JW STATION RD LN 1 | RUTTING IN CW | SELECTED | 2M | Minor Carriageway Repairs | Other | Permanent | 2020-03-31 21:31 | 28 Day Defect
836288 | 2020-03-03 21:31 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | TELFORD RD EB OPP JO PEVENSEY AVE | FAILED PATCH IN CW | SELECTED | 2M | Minor Carriageway Repairs | Failed patch : loss of material | Permanent | 2020-03-31 21:31 | 28 Day Defect
841423 | 2020-04-07 10:21 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | A406 TELFORD RD WB JUST PAST LOWER MAIDSTONE RD LN1 OF 3 | FAILED GULLY SURROUND | COMPLETED | 2H | Minor Carriageway Repairs | Cracking around ironwork | Permanent | 2020-04-14 10:21 | 7 Day Defect
841424 | 2020-04-07 10:21 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | A406 NCR WB JW BOUNDS GREEN RD ADJ TO CROSSING | LARGE CRACK | COMPLETED | 2M | Minor Carriageway Repairs | Cracking | Permanent | 2020-05-05 10:21 | 28 Day Defect
841425 | 2020-04-07 10:21 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | A406 NCR EB 60MTS B4 STATION RD LN1 OF 2 | CRACKING | COMPLETED | 2M | Minor Carriageway Repairs | Cracking | Permanent | 2020-05-05 10:21 | 28 Day Defect
841426 | 2020-04-07 10:21 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | A406 NCR EB 55MTS B4 STATION RD LN1 OF 2 | ROCKING MH AND FAILED CWAY | COMPLETED | 2M | Minor Carriageway Repairs | Cracking around ironwork | Permanent | 2020-05-05 10:21 | 28 Day Defect
841427 | 2020-04-07 10:21 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | A406 NCR JUST PAST JW MILTON GROVE LN1 OF 2 | FAILED GULLY SURROUND | COMPLETED | 2H | Minor Carriageway Repairs | Cracking around ironwork | Permanent | 2020-04-14 10:21 | 7 Day Defect
841428 | 2020-04-07 10:21 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | A406 TELFORD RD WB OS NO45 LN1 OF 2 | SHALLOW POTHOLE | COMPLETED | 2M | Minor Carriageway Repairs | Pothole | Permanent | 2020-05-05 10:21 | 28 Day Defect
841429 | 2020-04-07 10:21 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | A406 TELFORD RD WB JW BEXHILL RD | UNEVEN TACTILES | COMPLETED | 2M | Footways And Cycle Tracks | Slab profile : uneven/trips/gap | Permanent | 2020-05-05 10:21 | 28 Day Defect
842507 | 2020-04-15 04:50 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | A406 Pinkham Way WB, Past JW Bounds Green Road, OS BP Petrol station N11 2UU | pothole in c/w - repair | COMPLETED | 1 | Minor Carriageway Repairs | Pothole | Permanent | 2020-05-13 04:50 | Priority 1
842507 | 2020-04-15 04:50 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | A406 Pinkham Way WB, Past JW Bounds Green Road, OS BP Petrol station N11 2UU | pothole in c/w - repair | COMPLETED | 1 | Minor Carriageway Repairs | Pothole | Temporary | 2020-04-16 04:50 | Priority 1
847285 | 2020-05-08 02:32 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | A406 Telford rd WB jw Pevensey Avenue ln1 of 2 - | pothole around badly rocking TW cover - repair | COMPLETED | 1 | Minor Carriageway Repairs | Pothole | Permanent | 2020-05-09 02:32 | Priority 1
847294 | 2020-05-08 03:22 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | A406 Bowes rd WB ln1 approx 120 mts b4 Pymmes rd just past railbridge - | m/s pothole around mhc - repair | COMPLETED | 1 | Minor Carriageway Repairs | Pothole | Permanent | 2020-05-09 03:22 | Priority 1
848689 | 2020-05-16 07:14 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | A406 Telford rd WB os no81 on grass verge | LC DOOR OFF - REPAIR | COMPLETED | 1 | Road Lighting: Columns | Other | Permanent | 2020-06-13 07:14 | Priority 1
848689 | 2020-05-16 07:14 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | A406 Telford rd WB os no81 on grass verge | LC DOOR OFF - REPAIR | COMPLETED | 1 | Road Lighting: Columns | Other | Temporary | 2020-05-17 07:14 | Priority 1
848773 | 2020-05-18 05:31 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | A406 WB just inside jw Bounds Green rd - | POTHOLE IN WIDE CRAXK IN RD --REPAIR | COMPLETED | 1 | Minor Carriageway Repairs | Pothole | Permanent | 2020-06-15 05:31 | Priority 1
848773 | 2020-05-18 05:31 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | A406 WB just inside jw Bounds Green rd - | POTHOLE IN WIDE CRAXK IN RD --REPAIR | COMPLETED | 1 | Minor Carriageway Repairs | Pothole | Temporary | 2020-05-19 05:31 | Priority 1
848930 | 2020-05-19 05:11 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | A406 NCR WB 30mts past Bounds Green rd on fway | DISLODGED METAL BOLLARD AND SMASHED PAVING - RESET | COMPLETED | 1 | Footways And Cycle Tracks | Other | Permanent | 2020-05-20 05:11 | Priority 1
851183 | 2020-06-02 11:13 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | A406 TELFORD RD J/W BOUNDS GREEN RD EB | DEBRIS AND PGR DAMAGED | COMPLETED | 1 | Safety Bollards: Face/Structure/Fixings | Damaged/deformed | Permanent | 2020-06-30 11:13 | Priority 1
851183 | 2020-06-02 11:13 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | A406 TELFORD RD J/W BOUNDS GREEN RD EB | DEBRIS AND PGR DAMAGED | COMPLETED | 1 | Safety Bollards: Face/Structure/Fixings | Damaged/deformed | Temporary | 2020-06-03 11:13 | Priority 1
852045 | 2020-06-08 10:56 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | NORTH CIRCULAR RD JW MILTON GROVE; | SIGN OOL | COMPLETED | 2H | Signs: Lamp Failures | Lamp failure | Permanent | 2020-06-15 10:56 | 7 Day Defect
854304 | 2020-06-21 10:02 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | A406. near BP garage. on both eastbound and westbound carraigeways | potholes | COMPLETED | 1 | Concrete Carriageway Repairs | Pothole | Permanent | 2020-06-22 10:02 | Priority 1
854308 | 2020-06-21 10:53 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | A406 eb bounds green o/s bp petrol station | broken mhc | COMPLETED | 1 | Concrete Carriageway Repairs | Pothole | Permanent | 2020-06-22 10:53 | Priority 1
854349 | 2020-06-22 12:23 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | Garage1 North Circular Road, London | pothole | COMPLETED | 1 | Concrete Carriageway Repairs | Pothole | Permanent | 2020-06-23 12:23 | Priority 1
855167 | 2020-06-26 06:31 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | a406 Telford rd opp 59 40 mtrs b4 jo bexhill rd | pothole around gully in c/w repair | COMPLETED | 1 | Minor Carriageway Repairs | Pothole | Permanent | 2020-06-27 06:31 | Priority 1
855351 | 2020-06-29 02:00 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | telford rd just after pinkhamway bridge 50 yards b4 jw station rd | POTHOLE IN C/W REPAIR | COMPLETED | 1 | Minor Carriageway Repairs | Pothole | Permanent | 2020-06-30 02:00 | Priority 1
855352 | 2020-06-29 02:24 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | telford rd jb4 pinkhamway bridge 50 yards aftet jw boundsgreen rd ln 1 | 2 X POTHOLES IN CW REPAIR | COMPLETED | 1 | Minor Carriageway Repairs | Pothole | Permanent | 2020-06-30 02:24 | Priority 1
856459 | 2020-07-07 15:32 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | EB A406 JUST PAST JW MILTON GROVE | RUTTING | COMPLETED | 2M | Minor Carriageway Repairs | Other | Permanent | 2020-08-04 15:32 | 28 Day Defect
857266 | 2020-07-14 02:22 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | Pinkham way EB btw tunnel & BP lane 1 and 2 | POTHOLE IN C.W - REPAIR | COMPLETED | 1E | Minor Carriageway Repairs | Pothole | Permanent | 2020-08-11 02:22 | Priority 1 (ECO
860510 | 2020-08-04 13:35 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | EB A406 TELFORD RD AT JW MILTON GROVE | WORN KEEP CLEAR RD MARKING- LANE 1 & 2 | COMPLETED | 2M | Road Markings: | Wear | Permanent | 2020-09-01 13:35 | 28 Day Defect
860894 | 2020-08-06 02:42 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | WB A406 BOWES RD AROUND 20 MTRS PAST JW PALMERSTON RD | DAMAGED VRS BARRIERS - REPAIR | COMPLETED | 1 | Safety Fences: Metal/Concrete | Accident damage | Permanent | 2020-09-03 02:42 | Priority 1
860894 | 2020-08-06 02:42 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | WB A406 BOWES RD AROUND 20 MTRS PAST JW PALMERSTON RD | DAMAGED VRS BARRIERS - REPAIR | COMPLETED | 1 | Safety Fences: Metal/Concrete | Accident damage | Temporary | 2020-08-07 02:42 | Priority 1
861600 | 2020-08-10 20:55 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | A406 Telford road, JW Pevensey Avenue, WB, Lane 1. | Rocking loud manhole | COMPLETED | 1 | Covers,Gratings,Frames,Boxes | Difference in level with road | Permanent | 2020-09-07 20:55 | Priority 1
861600 | 2020-08-10 20:55 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | A406 Telford road, JW Pevensey Avenue, WB, Lane 1. | Rocking loud manhole | COMPLETED | 1 | Covers,Gratings,Frames,Boxes | Difference in level with road | Temporary | 2020-08-11 20:55 | Priority 1
863912 | 2020-08-26 01:37 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | A406 TELFORD RD, E/B, JW BOWES RD | 2 X DAMAGED PGR PANELS - REPAIR | COMPLETED | 1 | Safety Fences: Metal/Concrete | Damaged/deformed | Permanent | 2020-09-23 01:37 | Priority 1
863912 | 2020-08-26 01:37 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | A406 TELFORD RD, E/B, JW BOWES RD | 2 X DAMAGED PGR PANELS - REPAIR | COMPLETED | 1 | Safety Fences: Metal/Concrete | Damaged/deformed | Temporary | 2020-08-27 01:37 | Priority 1
865309 | 2020-09-04 15:32 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | EB A406 AT JW STATION RD | WEED GROWTH | COMPLETED | 2M | Planted Area: General | Weed | Permanent | 2020-10-02 15:32 | 28 Day Defect
865311 | 2020-09-04 15:32 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | BOWES RD-BOLLARD OPP WILMER WAY- YBJ ON CENTRAL ISLAND | BOLLARD FACING WRONG WAY | COMPLETED | 2H | Safety Bollards: Face/Structure/Fixings | Accident damage | Permanent | 2020-09-11 15:32 | 7 Day Defect
865308 | 2020-09-04 15:32 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | WB A406 IN YELLOW BOX JUNC AT JW BOUNDS GREEN RD | CW WEAR IN YBJ | COMPLETED | 2M | Minor Carriageway Repairs | Wear | Permanent | 2020-10-02 15:32 | 28 Day Defect
865310 | 2020-09-04 15:32 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | EB A406 BOWES RD IN YBJ AT JW WILMNER WAY | CW WEAR IN YBJ | COMPLETED | 2M | Minor Carriageway Repairs | Wear | Permanent | 2020-10-02 15:32 | 28 Day Defect
865430 | 2020-09-06 05:46 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | A406 station rd jw pinkham way n11 | flooding to clear in c/w | COMPLETED | 1E | Covers,Gratings,Frames,Boxes | Damaged/deformed | Permanent | 2020-10-04 05:46 | Priority 1 (ECO
865430 | 2020-09-06 05:46 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | A406 station rd jw pinkham way n11 | flooding to clear in c/w | COMPLETED | 1E | Covers,Gratings,Frames,Boxes | Damaged/deformed | Temporary | 2020-09-07 05:46 | Priority 1 (ECO
867758 | 2020-09-22 10:32 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | A406 PINKHAM WAY, E/B JW BOUNDS GREEN RD | BROKEN DOWN VEHICLE | COMPLETED | 1 | Concrete Carriageway Repairs | Accident damage | Permanent | 2020-09-23 10:32 | Priority 1
869645 | 2020-10-06 14:13 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | WB A406 TELFORD RD AT JW HASTINGS RD | WORN KEEP CLEAR RD MARKING-LANE 1 & 2 | COMPLETED | 2M | Road Markings: | Wear | Permanent | 2020-11-03 14:13 | 28 Day Defect
869646 | 2020-10-06 14:13 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | WB A406-TELFORD RD AT JW HASTINGS RD OS NO 67 | FAILING PATCH AROUND DOUBLE MHC IN LANE 1 | COMPLETED | 2M | Minor Carriageway Repairs | Cracking around ironwork | Permanent | 2020-11-03 14:13 | 28 Day Defect
870074 | 2020-10-08 20:07 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | WB A406 BOWES RD OS NO 326 LANE 1 | POTHOLE | COMPLETED | 1 | Concrete Carriageway Repairs | Pothole | Permanent | 2020-10-09 20:07 | Priority 1
870422 | 2020-10-10 14:44 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | station rd jw telford road a406 | floodinng | COMPLETED | 1 | Hw. Drain: Flooding | Flooding | Permanent | 2020-10-11 14:44 | Priority 1
871881 | 2020-10-19 23:21 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | REDBRIDGE RDBT BETWEEN EB A12 OFFSLIP AND NB A406 ONSLIP-ON EDGE OF LANE | Remove delineator on edge of lane 3. | COMPLETED | 1 | Safety Bollards: Face/Structure/Fixings | Damaged/deformed | Permanent | 2020-10-20 23:21 | Priority 1
871906 | 2020-10-20 03:37 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | EB, A406, just before the JW Station road, Enfield, just after the tunnel, opposite M&S, lane 1. | 1 x large c/w pothole | COMPLETED | 1 | Concrete Carriageway Repairs | Pothole | Permanent | 2020-10-21 03:37 | Priority 1
872488 | 2020-10-22 01:11 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | pinkham way jw station rd | flooding in c/w (defect on brorugh rd but flooding has spread and is affecting our rd) | COMPLETED | 1 | Hw. Drain: Flooding | Flooding | Permanent | 2020-10-23 01:11 | Priority 1
872496 | 2020-10-22 02:43 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | EB A406 TELFORD RD JW LOWER MAIDSTONE RD IN LN 1 | collapsed mhc to m/s | COMPLETED | 1 | Concrete Carriageway Repairs | Collapsed bank | Permanent | 2020-10-23 02:43 | Priority 1
872510 | 2020-10-22 04:27 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | WB A406 BOWES RD OS NO 368 -POTHOLE AROUND GULLY IN LANE 3 | Please make safe pothole around gully. | COMPLETED | 1 | Concrete Carriageway Repairs | Pothole | Permanent | 2020-10-23 04:27 | Priority 1
872511 | 2020-10-22 04:27 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | WB A406 BOWES RD OS NO 368 -POTHOLE AROUND GULLY IN LANE 3 | Please make safe pothole around gully. | COMPLETED | 1 | Concrete Carriageway Repairs | Pothole | Permanent | 2020-10-23 04:27 | Priority 1
872512 | 2020-10-22 04:40 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | WB A406 BOWES RD OS NO 368 -POTHOLE AROUND GULLY IN LANE 3 | Please make safe pothole around gully. | COMPLETED | 1 | Concrete Carriageway Repairs | Pothole | Permanent | 2020-10-23 04:40 | Priority 1
875601 | 2020-11-10 07:29 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | A406 NCR W/B JUST PAST J/W STATION ROAD | pothole around gully in c/w - repair | COMPLETED | 1 | Covers,Gratings,Frames,Boxes | Damaged/deformed | Permanent | 2020-12-08 07:29 | Priority 1
875601 | 2020-11-10 07:29 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | A406 NCR W/B JUST PAST J/W STATION ROAD | pothole around gully in c/w - repair | COMPLETED | 1 | Covers,Gratings,Frames,Boxes | Damaged/deformed | Temporary | 2020-11-11 07:29 | Priority 1
876087 | 2020-11-12 06:03 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | NB A406 TELFORD RD AROUND 15 MTRS B4 JW STATION RD IN LANE 1 OPP M&S PETROL STATION | UNBLOCK GULLY IN C/W | COMPLETED | 1 | Hw. Drain: Gullies, Catchpits | Other | Permanent | 2020-12-10 06:03 | Priority 1
876087 | 2020-11-12 06:03 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | NB A406 TELFORD RD AROUND 15 MTRS B4 JW STATION RD IN LANE 1 OPP M&S PETROL STATION | UNBLOCK GULLY IN C/W | COMPLETED | 1 | Hw. Drain: Gullies, Catchpits | Other | Temporary | 2020-11-13 06:03 | Priority 1
876341 | 2020-11-13 08:45 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | a406 TELFORD RD BY HAUNELTS GROVES OVER HEAD BRIDGE NEAREST JW WILMER WAY | RTC - CAD: 680 - LARGE SPILLAGE 40SQM AREA TO CLEAN | COMPLETED | 1E | Sweeping And Cleansing | Other | Permanent | 2020-12-11 08:45 | Priority 1 (ECO
882314 | 2021-01-05 15:50 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | TELFORD RD ON CI JB4 BOUNDS GREEN | DAMAGED PGR | COMPLETED | 2M | Street Furniture | Accident damage | Permanent | 2021-02-02 15:50 | 28 Day Defect
884797 | 2021-01-24 15:03 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | A406 TELFORD ROAD WB JW MILTON GROVE | RTC - CAR HIT LC - REPAIR | COMPLETED | 1E | Road Lighting: Columns | Accident damage | Permanent | 2021-02-21 15:03 | Priority 1 (ECO
884797 | 2021-01-24 15:03 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | A406 TELFORD ROAD WB JW MILTON GROVE | RTC - CAR HIT LC - REPAIR | COMPLETED | 1E | Road Lighting: Columns | Accident damage | Temporary | 2021-01-25 15:03 | Priority 1 (ECO
885310 | 2021-01-27 05:28 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | NEAR 101 EVESHAM RD, N11 2RL | POTHOLE, ROAD HAS LIFTED AND THERE IS STANDING WATER - SUSPECTED BURST WATER PIPE | COMPLETED | 1 | Hw. Drain: Gullies, Catchpits | Flooding | Permanent | 2021-02-24 05:28 | Priority 1
885310 | 2021-01-27 05:28 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | NEAR 101 EVESHAM RD, N11 2RL | POTHOLE, ROAD HAS LIFTED AND THERE IS STANDING WATER - SUSPECTED BURST WATER PIPE | COMPLETED | 1 | Hw. Drain: Gullies, Catchpits | Flooding | Temporary | 2021-01-28 05:28 | Priority 1
885312 | 2021-01-27 05:56 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | A406 TELFORD RD, E/B, 150 YARDS PAST STATION RD, UNDER RAILWAY BRIDGE | LARGE, DANGEROUS POTHOLE AROUND MHC NEEDS TO BE MADE SAFE. IPV ALSO NEEDED. | COMPLETED | 1 | Concrete Carriageway Repairs | Pothole | Permanent | 2021-02-24 05:56 | Priority 1
885312 | 2021-01-27 05:56 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | A406 TELFORD RD, E/B, 150 YARDS PAST STATION RD, UNDER RAILWAY BRIDGE | LARGE, DANGEROUS POTHOLE AROUND MHC NEEDS TO BE MADE SAFE. IPV ALSO NEEDED. | COMPLETED | 1 | Concrete Carriageway Repairs | Pothole | Temporary | 2021-01-28 05:56 | Priority 1
886444 | 2021-02-03 21:51 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | NORTH CIRCULAR RD JW LOWER MAIDSTONE RD; S2 - GIVE WAY | SIGN OOL | COMPLETED | 2H | Signs: Lamp Failures | Lamp failure | Permanent | 2021-02-10 21:51 | 7 Day Defect
887797 | 2021-02-15 20:26 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | WB A406 Telford road, WB, Lane 1, JW Pevensey Avenue | ROCKING MHC IN CW | INSTRUCTED | 1 | Covers,Gratings,Frames,Boxes | Cracking around ironwork | Permanent | 2021-03-15 20:26 | Priority 1
887797 | 2021-02-15 20:26 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | WB A406 Telford road, WB, Lane 1, JW Pevensey Avenue | ROCKING MHC IN CW | INSTRUCTED | 1 | Covers,Gratings,Frames,Boxes | Cracking around ironwork | Temporary | 2021-02-16 20:26 | Priority 1
888088 | 2021-02-17 08:32 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | 59 Telford Road North Circular Road, London, N11 2RH | SUNKEN MHC IN C.W VERY NOISY - REPAIR | COMPLETED | 1 | Covers,Gratings,Frames,Boxes | Damaged/deformed | Permanent | 2021-03-17 08:32 | Priority 1
888088 | 2021-02-17 08:32 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | 59 Telford Road North Circular Road, London, N11 2RH | SUNKEN MHC IN C.W VERY NOISY - REPAIR | COMPLETED | 1 | Covers,Gratings,Frames,Boxes | Damaged/deformed | Temporary | 2021-02-18 08:32 | Priority 1
888107 | 2021-02-17 09:11 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | Telford rd WB JW pevensey Ave | SUNKNE MHC IN C/W - REPAIR | COMPLETED | 1 | Minor Carriageway Repairs | Cracking | Permanent | 2021-03-17 09:11 | Priority 1
888107 | 2021-02-17 09:11 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | Telford rd WB JW pevensey Ave | SUNKNE MHC IN C/W - REPAIR | COMPLETED | 1 | Minor Carriageway Repairs | Cracking | Temporary | 2021-02-18 09:11 | Priority 1
889583 | 2021-03-02 01:50 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | A406 North circular road, EB, lane 1, at the exit of Pinkham Way, just before the JW Station road. | FAILING MHC SURROUND | COMPLETED | 1 | Concrete Carriageway Repairs | Other | Permanent | 2021-03-30 01:50 | Priority 1
889583 | 2021-03-02 01:50 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | A406 North circular road, EB, lane 1, at the exit of Pinkham Way, just before the JW Station road. | FAILING MHC SURROUND | COMPLETED | 1 | Concrete Carriageway Repairs | Other | Temporary | 2021-03-03 01:50 | Priority 1
889596 | 2021-03-02 04:29 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | A406 Telford road, EB, Lane 1, directly under the bridge, just before the JW Hastings Road | Failing manhole cover surround | COMPLETED | 1 | Concrete Carriageway Repairs | Other | Permanent | 2021-03-30 04:29 | Priority 1
889596 | 2021-03-02 04:29 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | A406 Telford road, EB, Lane 1, directly under the bridge, just before the JW Hastings Road | Failing manhole cover surround | COMPLETED | 1 | Concrete Carriageway Repairs | Other | Temporary | 2021-03-03 04:29 | Priority 1
889855 | 2021-03-03 12:06 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | N CIRCULAR RD RD JW PEVENSEY AVENUE | COLUMN OOL | INSTRUCTED | 2H | Road Lighting: Lamp Failures | Lamp failure | Permanent | 2021-03-10 12:06 | 7 Day Defect
889856 | 2021-03-03 12:06 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | N CIRCULAR RD WB OPP LC B59 | COLUMN OOL | INSTRUCTED | 2H | Road Lighting: Lamp Failures | Lamp failure | Permanent | 2021-03-10 12:06 | 7 Day Defect
890830 | 2021-03-16 06:22 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | a406 Telford rd wb jw Bounds Green rd | failed patch in cw ln1- yellow box | COMPLETED | 1 | Concrete Carriageway Repairs | Failed patch : difference in level | Permanent | 2021-04-13 06:22 | Priority 1
890830 | 2021-03-16 06:22 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | a406 Telford rd wb jw Bounds Green rd | failed patch in cw ln1- yellow box | COMPLETED | 1 | Concrete Carriageway Repairs | Failed patch : difference in level | Temporary | 2021-03-17 06:22 | Priority 1
891156 | 2021-03-19 00:56 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | Telford rd eb 10 Myra after Pinkham way bridge by central res | large pothole in lane 2- REPAIR | COMPLETED | 1 | Minor Carriageway Repairs | Pothole | Permanent | 2021-04-16 00:56 | Priority 1
891156 | 2021-03-19 00:56 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | Telford rd eb 10 Myra after Pinkham way bridge by central res | large pothole in lane 2- REPAIR | COMPLETED | 1 | Minor Carriageway Repairs | Pothole | Temporary | 2021-03-20 00:56 | Priority 1
891158 | 2021-03-19 01:40 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | Telford rd eb opp bp garage 50 MTRS after Pinkham way bridge | large pothole X2 potholes in Ln 3 | COMPLETED | 1 | Minor Carriageway Repairs | Pothole | Permanent | 2021-04-16 01:40 | Priority 1
891158 | 2021-03-19 01:40 | 0000A406_2/00080 | A406,TELFORD RD,,(GAS WORKS TO JUNCT BOWES RD),N11 | Telford rd eb opp bp garage 50 MTRS after Pinkham way bridge | large pothole X2 potholes in Ln 3 | COMPLETED | 1 | Minor Carriageway Repairs | Pothole | Temporary | 2021-03-20 01:40 | Priority 1