## Batch Cover Sheet
Ultra Low Emission Zone Extension - Cameras on Traffic Signal Poles - Signal Pole Review
Batch | 35
Revision | Submission Date | Project Manager / Designer commentary | Reviewer commentary | Status
1 | 2022-03-08 | Batch 035 Initial submission | Site 10540 should be in Conversions as it hosts camera 27/605994 already. This camera has not been flagged for removal in the Conversion Status List.xlsx provided. | Requires Review | Approved
2 | 2022-03-16 | Site 10540 descoped pending clarification | See comments on potention conflict with SCOOT detection for sites 10720 and 10740. | Approved | Requires Review
Please save this workbook with a filename updated for the batch number and revision number e.g. "Traffic Signal Sites - Pole Review Sheet - BATCH 001 Rev2.xlsx"
For revisions beyond revision 1, add Submission Date to begin.

## ATS Posts Review
Ultra Low Emission Zone Extension - Cameras on Traffic Signal Poles - Signal Pole Review
Batch | 35 |  | Reviewer | Jack Pruett
Number of cameras | 10 | Count = 10 | Review Date | 2022-03-16
Revision | 2 |  | Approver | Neil Davis
Date (dd/mm/yyyy): | 2022-03-16 |  | Approval Date | 2022-03-16
|  |  | Status | Approved
To be completed by designer/project manager |  |  |  | Traffic Control Engineering review only
Borough | Street | Camera ID | Traffic Signal Site Number | Pole Number | Year of Installation | Date of Periodic Condition Inspection | Condition Score from SFM Database |  | Reviewer Commentary (if required) | Response from previous Revision
[7 empty] | Score | Description
Islington | Palmer Place - Mackenzie Road - B515 Liverpool Road | 1072 | 03/000024 | 9 | 2015-08-06 | 2021-05-06 | 4 | Good | Camera bracket may need to be mounted on mounting point parallel to the kerb here, rather than perpendicular, to avoid obstructing line of comms from Access Point to Magnetometer.
Barnet | Cricklewood Lane - Lichfield Road - Claremont Road | 1074 | 30/000003 | 2 | 2020-07-09 | 2021-01-27 | 5 | Excellent | Pole 2 will require SCOOT Access Point to be re-mounted to allow ULEZ camera to be mounted from rear of pole as per OFDS. As site is Siemens ELV controller could be done by TCMS2 contractor when cable is run.
City of London | Cannon Street - Walbrook - Dowgate Hill | 1078 | 00/000117 | 8 | 2012-04-21 | 2021-08-19 | 3 | Acceptable
Islington | HIGHBURY GROVE BY BAALBEC ROAD | 1086 | 03/000121 | 1 | 2020-02-21 | 2021-04-30 | 4 | Good
Hackney | A107 MARE STREET - KING EDWARD'S ROAD - WESTGATE STREET | 1087 | 04/000014 | 16 | 2015-12-15 | 2021-11-30 | 4 | Good
Hackney | WILSON STREET - SUN STREET | 1095 | 04/000006 | 4 | 2018-11-27 | 2021-12-22 | 5 | Excellent
Islington | STROUD GREEN RD - CROUCH HILL - MOUNT PLEASANT CRESCENT - STAPLETON HALL RD | 1101 | 03/000019 | 2 | 2014-06-27 | 2021-04-29 | 4 | Good | Site Address corrected from A103 Hornsey Road - Hanley Road - Marlborough Road
Brent | A407 High Road Willesden - Brondesbury Park | 1108 | 28/000083 | 6 | 2003-12-22 | 2021-01-12 | 4 | Good | Site Address corrected from A4003 High Road Willesden - A407 Walm Lane
Tower Hamlets | WHITECHAPEL ROAD BY FIELDGATE STREET SOUTHWEST BOUND | 1119A | 05/000241 | 1 | 2015-09-14 | 2021-10-20 | 5 | Excellent
Tower Hamlets | WHITECHAPEL ROAD BY FIELDGATE STREET SOUTHWEST BOUND | 1119B | 05/000241 | 3 | 2015-09-14 | 2021-10-20 | 5 | Excellent
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-

## POLE CONDITION AT PI
Maintenance Date | Audit Date | Ver. | Site | Suffix | Bor. | Status | Cont. | Contract Number | Engineer Name | Audit Name | EQ 5.3 | AQ 5.3 | EQ 5.3.1 | AQ 5.3.1 | Final Rating | Final Rating Description
2021-05-06 |  | 1 | 03/000024 | /U | 3 | COMPLETE |  |  |  |  | Yes |  | 4 |  | 4 | Good
2021-01-27 |  | 1 | 30/000003 | / | 30 | COMPLETE |  |  |  |  | Yes |  | 5 |  | 5 | Excellent
2021-08-19 |  | 1 | 00/000117 | /U | 0 | COMPLETE |  |  |  |  | Yes |  | 3 |  | 3 | Acceptable
2021-04-30 |  | 1 | 03/000121 | /U | 3 | COMPLETE |  |  |  |  | Yes |  | 4 |  | 4 | Good
2021-11-30 |  | 1 | 04/000014 | /U | 4 | COMPLETE |  |  |  |  | Yes |  | 4 |  | 4 | Good
2021-12-22 |  | 1 | 04/000006 | /U | 4 | COMPLETE |  |  |  |  | Yes |  | 5 |  | 5 | Excellent
2021-04-29 |  | 1 | 03/000019 | /U | 3 | COMPLETE |  |  |  |  | Yes |  | 4 |  | 4 | Good
2021-01-12 |  | 1 | 28/000083 | /U | 28 | COMPLETE |  |  |  |  | Yes |  | 4 |  | 4 | Good
2021-10-20 |  | 1 | 05/000241 | /U | 5 | COMPLETE |  |  |  |  | Yes |  | 5 |  | 5 | Excellent
[15 empty] | N/A | -
[15 empty] | N/A | -
[15 empty] | N/A | -
[15 empty] | N/A | -
[15 empty] | N/A | -
[15 empty] | N/A | -
[15 empty] | N/A | -
[15 empty] | N/A | -
[15 empty] | N/A | -
[15 empty] | N/A | -
[15 empty] | N/A | -
[15 empty] | N/A | -
[15 empty] | N/A | -
[15 empty] | N/A | -
[15 empty] | N/A | -

## POLE INSTALLATION DATES
Site | Suffix | Location | Avail.System | Eq. Code | E. Code Description | Units | Easting | Northing | Install Date | ControllerInst. Date | SiteType
00/000117 | /U | CANNON STREET - WALBROOK - DOWGATE HILL | ATS | PFU001 | Black Coated Formed Pole (4.0m) Unsp | 6 | 532602.918 | 180918.845 | 2012-04-21 | 2012-04-21 | MP
00/000117 | /U | CANNON STREET - WALBROOK - DOWGATE HILL | ATS | PCU001 | Black Coated Pole (4.0m) Unsp | 10 | 532602.918 | 180918.845 | 2012-04-21 | 2012-04-21 | MP
00/000117 | /U | CANNON STREET - WALBROOK - DOWGATE HILL | ATS | PCH001 | Black Coated Pole (2.0m) Unsp | 1 | 532602.918 | 180918.845 | 2012-04-21 | 2012-04-21 | MP
03/000019 | /U | STROUD GREEN RD - CROUCH HILL - MOUNT PLEASANT CRESCENT - STAPLETON HALL RD | ATS | PCU001 | Black Coated Pole (4.0m) Unsp | 11 | 530723.49 | 187437.04 | 2014-06-27 | 2014-06-27 | MP
03/000019 | /U | STROUD GREEN RD - CROUCH HILL - MOUNT PLEASANT CRESCENT - STAPLETON HALL RD | ATS | PCH001 | Black Coated Pole (2.0m) Unsp | 1 | 530723.49 | 187437.04 | 2014-06-27 | 2014-06-27 | MP
03/000024 | /U | PALMER PLACE - MACKENZIE ROAD - B515 LIVERPOOL ROAD | ATS | PCU001 | Black Coated Pole (4.0m) Unsp | 15 | 531084.95 | 185103.31 | 2015-08-06 | 2015-08-06 | MP
03/000121 | /U | HIGHBURY GROVE BY BAALBEC ROAD | ATS | PFU001 | Black Coated Formed Pole (4.0m) Unsp | 2 | 531973.21 | 185073.08 | 2020-02-21 | 2020-02-21 | PD
04/000006 | /U | WILSON STREET - SUN STREET | ATS | PCU001 | Black Coated Pole (4.0m) Unsp | 8 | 532944.86 | 181894.86 | 2018-11-27 | 2018-11-27 | MP
04/000014 | /U | A107 MARE STREET - KING EDWARDS ROAD - WESTGATE STREET | ATS | PFU001 | Black Coated Formed Pole (4.0m) Unsp | 1 | 534849.14 | 183905.87 | 2015-12-15 | 2015-12-15 | MP
04/000014 | /U | A107 MARE STREET - KING EDWARDS ROAD - WESTGATE STREET | ATS | PCU001 | Black Coated Pole (4.0m) Unsp | 13 | 534849.14 | 183905.87 | 2015-12-15 | 2015-12-15 | MP
04/000014 | /U | A107 MARE STREET - KING EDWARDS ROAD - WESTGATE STREET | ATS | PCH001 | Black Coated Pole (2.0m) Unsp | 2 | 534849.14 | 183905.87 | 2015-12-15 | 2015-12-15 | MP
05/000241 | /U | WHITECHAPEL ROAD BY FIELDGATE STREET | ATS | PCU001 | Black Coated Pole (4.0m) Unsp | 3 | 534191.7 | 181576.3 | 2015-09-14 | 2015-09-14 | PD
05/000241 | /U | WHITECHAPEL ROAD BY FIELDGATE STREET | ATS | PCT001 | Black Coated Pole (4.85m) Unsp | 1 | 534191.7 | 181576.3 | 2015-09-14 | 2015-09-14 | PD
05/000241 | /U | WHITECHAPEL ROAD BY FIELDGATE STREET | ATS | PCM000 | Galvanised Steel Pole (Mast Arm) Unsp | 1 | 534191.7 | 181576.3 | 2015-09-14 | 2015-09-14 | PD
28/000083 | /U | A407 HIGH ROAD WILLESDEN - BRONDESBURY PARK | ATS | PCU001 | Black Coated Pole (4.0m) Unsp | 12 | 522893.72 | 184623.23 | 2003-12-22 | 2003-12-22 | MP
30/000003 | / | CRICKLEWOOD LANE - LICHFIELD ROAD - CLAREMONT ROAD | ATS | PFU001 | Black Coated Formed Pole (4.0m) Unsp | 2 | 524068.79 | 185934.18 | 2020-07-09 | 2020-07-09 | MP
30/000003 | / | CRICKLEWOOD LANE - LICHFIELD ROAD - CLAREMONT ROAD | ATS | PCU001 | Black Coated Pole (4.0m) Unsp | 7 | 524068.79 | 185934.18 | 2020-07-09 | 2020-07-09 | MP