## Sheet1
Inspection Date | Reference Number | Feature | BRS Code | From Station | Road | Meterage | Distance | Priority | Remarks | Report Number | Completion Due Date | Work Completed | LUL Completion Date
2020-12-15 | TC7497 | Tree Compartment | M064 | Northwood | NB | 56 | 78 | 1 | 15/12/2020: Fell dead and diseased Sycamores (at least 3 trees) on boundary with Library at approx. 50-12m. | ML1813 | 2021-02-15
2020-12-15 | TC7491 | Tree Compartment | M064 | Northwood | NB | 337 | 133 | 1 | 15/12/2020: Fell dead Sycamore and two Birch at approx. 430-445m. | ML1813 | 2021-02-15 | Completed | 2021-02-04
2020-12-15 | NWST7238 | NW Structure | M064 | Northwood | NB | 605 | 12 | 4 | 15/12/2020: Liaise with owner concerning deadwood in mature Oak overhanging LU at approx. 623m. | ML1813 | 2021-12-15
2020-12-15 | TC7489 | Tree Compartment | M064 | Northwood | NB | 614 | 60 | 1 | 15/12/2020: Fell two dead Birch at approx. 650m. | ML1813 | 2021-02-15 | Completed | 2021-01-11
2020-12-15 | F8899 | Fence | M064 | Northwood | NB | 796 | 191 | 1 | 15/12/2020: Cut back to boundary third party tree on fence at approx. 860m. | ML1813 | 2021-02-15 | Completed | 2021-01-11
2020-12-15 | T11815 | Tree | M064 | Northwood | NB | 815 | 0 | 2 | 15/12/2020: Remove deadwood from Oak over fence at approx. 815m. | ML1813 | 2021-04-15
2020-12-15 | TC10570 | Tree Compartment | M064 | Northwood | NB | 816 | 64 | 2 | 15/12/2020: Cut back overhang to fence at approx. 830m. | ML1813 | 2021-04-15
2020-12-15 | NWST7240 | NW Structure | M064 | Northwood | NB | 900 | 56 | 3 | 15/12/2020: Cut back third party overhang to track at approx. 945m. | ML1813 | 2021-06-15 | Completed | 2021-02-04
2020-12-15 | F8828 | Fence | M064 | Northwood | NB | 1444 | 581 | 3 | 15/12/2020: Cut back third party overhang from fence at approx. 1620m. | ML1813 | 2021-06-15
2020-12-15 | U7786 | Understorey Misc | M064 | Northwood | NB | 1446 | 22 | 2 | 15/12/2020: Clear snapped branch from Willow and pollard remainder at approx. 1450m. | ML1813 | 2021-04-15
2020-12-15 | TC9482 | Tree Compartment | M064 | Northwood | NB | 1490 | 488 | 3 | 15/12/2020: Cut back third party overhang to fence @ 1560, 1700 and 1910 and throughout compartment. | ML1813 | 2021-06-15
2020-12-15 | T14072 | Tree | M064 | Northwood | NB | 1570 | 0 | 2 | 15/12/2020: Remove deadwood over LU from third party Scots Pine at approx. 1570m. | ML1813 | 2021-04-15
2020-12-15 | T13012 | Tree | M064 | Northwood | NB | 1579 | 0 | 3 | 15/12/2020: Pollard Ash @ 1620 and cut back overhang to track at approx. 1570-1620. | ML1813 | 2021-06-15
2020-12-15 | TC7479 | Tree Compartment | M064 | Northwood | NB | 1803 | 25 | 2 | 15/12/2020: Fell Hazel collapsed on fence and coppice remainder of stool at approx. 1810m. | ML1813 | 2021-04-15 | Completed
2020-12-15 | U7472 | Understorey Misc | M064 | Northwood | NB | 1828 | 51 | 2 | 15/12/2020: Fell Buddleia collapsed on fence at approx. 1870m. | ML1813 | 2021-04-15
2020-12-15 | TC10575 | Tree Compartment | M064 | Northwood | NB | 1962 | 52 | 3 | 15/12/2020: Cut back overhang to track at approx. 2000m. | ML1813 | 2021-06-15 | Completed | 2021-02-04
2020-12-15 | T10187 | Tree | M064 | Northwood | NB | 2012 | 0 | 3 | 15/12/2020: Fell Hornbeam pollard with decaying bole at approx. 2012m. | ML1813 | 2021-06-15 | Completed | 2021-02-04
2020-12-15 | U7239 | Understorey Misc | M064 | Moor Park | SB | 261 | 257 | 2 | 15/12/2020: Fell diseased regen, Hornbeam @ 402m and Willow @ 445m. | ML1813 | 2021-04-15 | Completed | 2021-01-11
2020-12-15 | NWDR7056 | NW Drainage | M064 | Moor Park | SB | 320 | 320 | N/A | 15/12/2020: Pooling water - ditch overwhelmed at approx. 630-700m. | ML1813 | N/A | Completed
2020-12-15 | NWFL7308 | NW Fenceline | M064 | Moor Park | SB | 705 | 410 | 2 | 15/12/2020: Cut back third party overhang to fence at approx. 880m. | ML1813 | 2021-04-15
2020-12-15 | TC10555 | Tree Compartment | M064 | Moor Park | SB | 957 | 10.5 | 3 | 15/12/2020: Dutch Elm disease at approx. 960m fell dead stems. | ML1813 | 2021-06-15
2020-12-15 | T11628 | Tree | M064 | Moor Park | SB | 972 | 0 | 2 | 15/12/2020: Fell stem growing diagonally over fence a approx. 970m. | ML1813 | 2021-04-15 | Completed | No Date
2020-12-15 | T11624 | Tree | M064 | Moor Park | SB | 1003 | 0 | 2 | 15/12/2020: Remove dead limb over fence and fell nearby diagonal stems growing over fence at approx. 1008m. | ML1813 | 2021-04-15 | Completed | No Date
2020-12-15 | TC10558 | Tree Compartment | M064 | Moor Park | SB | 1078 | 14 | 2 | 15/12/2020: Cut back overhang from fence at approx. 1080m. | ML1813 | 2021-04-15 | Completed | No Date
2020-12-15 | G7326 | Gate | M064 | Moor Park | SB | 1126 | 0 | 1 | 15/12/2020: Gate sticking, needs significant force to open/close. | ML1813 | 2021-02-15 | Completed | 2021-01-07
2020-12-15 | T11613 | Tree | M064 | Moor Park | SB | 1291 | 0 | 1 | 15/12/2020: Oak, remove deadwood over fence and footpath at approx. 1292m. | ML1813 | 2021-02-15 | Completed | 2021-01-11
2020-12-15 | TC10561 | Tree Compartment | M064 | Moor Park | SB | 1319 | 89.5 | 3 | 15/12/2020: Remove low laterals over fence at approx. 1390m. | ML1813 | 2021-06-15 | Completed | 2021-01-11
2020-12-15 | TC7243 | Tree Compartment | M064 | Moor Park | SB | 1407 | 46 | 1 | 15/12/2020: Oak, remove deadwood over fence and footpath at approx. 1412m. | ML1813 | 2021-02-15 | Completed | 2021-01-11
2020-12-15 | F8823 | Fence | M064 | Moor Park | SB | 1467 | 516 | 2 | 15/12/2020: Clear fence strip to one metre width at approx. 1790m. | ML1813 | 2021-04-15 | Completed
2020-12-15 | TC7244 | Tree Compartment | M064 | Moor Park | SB | 1470 | 242 | 2 | 15/12/2020: Various trees on or over fence, Cherry @1545, Hawthorns @ 1590 & 1622. Lateral @1668, tree @1698. | ML1813 | 2021-04-15 | Completed | 2021-02-04
2020-12-15 | T11577 | Tree | M064 | Moor Park | SB | 1821 | 0 | 1 | 15/12/2020: Fell dead Oak at approx. 1820m. | ML1813 | 2021-02-15 | Completed | 2021-01-11
2020-12-15 | T11573 | Tree | M064 | Moor Park | SB | 1862 | 0 | 1 | 15/12/2020: Fell dead Sycamore at approx. 1965m. | ML1813 | 2021-02-15 | Completed
2020-12-15 | TC7251 | Tree Compartment | M064 | Moor Park | SB | 1937 | 29 | 1 | 15/12/2020: Remove snapped out limb from Ash by gate. | ML1813 | 2021-02-15 | Completed | 2021-01-11
2021-03-11 | TC7497 | Tree Compartment | M064 | Northwood | NB | 56 | 78 | 1 | 11/03/2021: Fell dead and diseased Sycamores (at least 3 trees) on boundary with Library at approx. 50-120m. | ML1829 | 2021-05-11
2021-03-11 | TC8021 | Tree Compartment | M064 | Northwood | NB | 306 | 306 | 2 | 11/03/2021: Cut back trees overhanging cablerun. | ML1829 | 2021-07-11
2021-03-11 | T11634 | Tree | M064 | Moor Park | SB | 549 | 0 | 2 | 11/03/2021: Face back overhang to track. | ML1829 | 2021-07-11 | Completed
2021-03-11 | T17044 | Tree | M064 | Moor Park | SB | 1169 | 0 | 1 | 11/03/2021: Basal decay, fell. | ML1829 | 2021-05-11 | Completed
2021-03-11 | TC7251 | Tree Compartment | M064 | Moor Park | SB | 1937 | 29 | 2 | 11/03/2021: Remove litter. | ML1829 | 2021-07-11
2021-03-11 | TC7252 | Tree Compartment | M064 | Moor Park | SB | 2000 | 48 | 3 | 11/03/2021: Cut ivy. | ML1829 | 2021-09-11
2021-06-09 | TC8023 | Tree Compartment | M064 | Northwood | NB | 56 | 78 | 4 | Tree leaning over track, fell | ML1842 | 2021-09-09
2021-06-09 | TC7488 | Tree Compartment | M064 | Northwood | NB | 744 | 40 | 3 | Dead/dying tree over fence at approx 740m. Fell | ML1842 | 2021-06-09 | Completed
2021-06-09 | NWCR7077 | Nonwoody | M064 | Northwood | NB | 970 | 0 | 3 | Face back all overhanging trees. Some trees behind fence are on LU land | ML1842 | 2021-06-09
2021-06-09 | NWCR7078 | Nonwoody | M064 | Northwood | NB | 1380 | 0 | 3 | Faceback where overhanging cablerun | ML1842 | 2021-06-09
2021-06-09 | T17040 | Individual Tree | M064 | Northwood | NB | 1457 | 0 | 4 | Snapped limb overhanging fence, remove. Remove dead wood from tree | ML1842 | 2021-09-09
2021-06-09 | T11634 | Individual Tree | M064 | Moor Park | SB | 549 | 0 | 4 | Face back overhang to track, cut ivy on oaks in the area | ML1842 | 2021-09-09 | Completed
2021-06-09 | T11622 | Individual Tree | M064 | Moor Park | SB | 1133 | 0 | 2 | Cut ivy | ML1842 | 2023-06-09
2021-06-09 | TC7244 | Tree Compartment | M064 | Moor Park | SB | 1470 | 242 | 4 | Fell dead tree near fence at approx 1645m | ML1842 | 2021-09-09
2021-06-09 | CSP7008 | Controlled Species | M064 | Moor Park | SB | 1782 | 26 | 4 | Treat Japanese Knotweed | ML1842 | 2021-09-09
2021-09-08 | TC8023 | Tree Compartment | M064 | Northwood | NB | 56 | 78 | 4 | Tree leaning over track, fell | ML1861 | 2021-12-08
2021-09-08 | F4382 | Fence | M064 | Northwood | NB | 459 | 0 | 3 | Fence post bended at approx 540m, replace or repair | ML1861 | 2022-09-08
2021-09-08 | T11634 | Individual Tree | M064 | Moor Park | SB | 549 | 0 | 4 | Faceback tree overhanging track. | ML1861 | 2021-12-08 | Completed
2021-09-08 | CSP7008 | Controlled Species | M064 | Moor Park | SB | 1782 | 26 | 4 | Treat Japanese Knotweed | ML1861 | 2021-12-08
2021-12-08 | NWCR7076 | Nonwoody | M064 | Northwood | NB | 49 | 0 | 3 | Face back where overhanging cablerun. Consider felling LU trees that are overhanging | ML1878 | 2022-12-08
2021-12-08 | TC8021 | Tree Compartment | M064 | Northwood | NB | 306 | 306 | 4 | Trees at approx. 400 metres dropping branches. Prune or fell those near cableruns. | ML1878 | 2022-03-08
2021-12-08 | NWCR7077 | Nonwoody | M064 | Northwood | NB | 970 | 0 | 3 | Face back all overhanging trees. Some trees behind fence are on LU land | ML1878 | 2022-12-08
2021-12-08 | TC7481 | Tree Compartment | M064 | Northwood | NB | 1572 | 59 | 3 | Cut ivy | ML1878 | 2022-12-08
2021-12-08 | TC10575 | Tree Compartment | M064 | Northwood | NB | 1962 | 52 | 3 | Cut ivy | ML1878 | 2022-12-08
2021-12-08 | T11628 | Individual Tree | M064 | Moor Park | SB | 972 | 0 | 2 | Lateral tree over third party garden, fell | ML1878 | 2023-12-08
2021-12-08 | TC7252 | Tree Compartment | M064 | Moor Park | SB | 2000 | 48 | 3 | Cut ivy | ML1878 | 2022-12-08