## Sheet1
Snag List - Section 5
Item | Sheet | Furniture | Location / Ref. | Description
01 | 2 | Roundel | A501 Marylebone Rd. in front of Sheringham House | triple Roundels missing
Snag List - Section 6
Item | Sheet | Furniture | Location / Ref. | Description
01 | 1 | Roundel | Boundary Road | Roundel descoped due the proximity of oncoming 30mph speed limit road
02 | 1 | Signage | Finchley Road (Western footway side) jw Boundary Road | Signs to be moved away from the face kerb to avoid vehicle collision
03 | 1 | Signage | Finchley Road (Eastern footway side) jw Boundary Road | Signs to be moved away from the face kerb to avoid vehicle collision
04 | 3 | Signage | Finchley Road in front of Wellington Road (C3_RS01) | 30mph camera sign to be removed
05 | 3 | Signage | Circus Road - Northern side (C3_RS04) | 30mph sign to be removed
06 | 3 | Signage | Circus Road - Northern side | 20mph Ø600mm to be removed and replace by a 20mph Ø450mm
07 | 3 | Signage | Circus Road - Southern side | 20mph Ø600mm to be removed and replace by a 20mph Ø450mm
08 | 3 | Roundel | Wellington Road (Eastern footway side) jw Wellington Place | One Roundel missing
09 | 3 | Signage | Wellington Road (Eastern footway side) jw Wellington Place | 20mph Ø600mm to be removed and replace by a 20mph Ø450mm
10 | 3 | Signage | Wellington Road (Western footway side) jw Wellington Place (Northern footway side) | 20mph Ø600mm to be removed and replace by a 20mph Ø450mm
11 | 3 | Signage | Wellington Road (Western footway side) jw Wellington Place (Southern footway side) | 20mph Ø600mm to be removed and replace by a 20mph Ø450mm
12 | 5 | Signage | Hanover Gate | Cycle sign not properly installed
13 | 7 | Signage | Gloucester Place jw Dorset Close (C7_PS13) | Signs installed under the minimum height of 2,1m and not properly installed
Snag List - Section 7
Item | Sheet | Furniture | Location / Ref. | Description
01 | 3 | Roundel | Claredon Terrace | One Roundel is missing
02 | 3 | Signage | Northwick Terrace | Sign is installed but it is misshaped/ bent.
03 | 4 | Signage | Oak Tree Road | Sign is installed, however, the sign is not facing the upcoming vehicles. It cannot be amended unless the scaffolding is removed.
Snag List - Section 9
Item | Sheet | Furniture | Location / Ref. | Description
01 | 1 | Sign Post | Traffic island on Oxford Street | Maintenance required. Post is a bit loos and bouncing
02 | 1 | Signage | Tyburn Way (C1_PS06) | Missing 20mph Ø450mm sign
03 | 1 | Signage | Marble Arch (Southern footway side) (C1_PS08) | Missing 20mph Ø450mm sign
04 | 1 | Signage | Green Street jw Park Lane (C1_PS13) | Missing 20mph Ø600mm sign
05 | 1 | Signage | Park Lane jw Green Street (C1_PS12) | Maintenance required. Post and sign might have been damaged by a vehicle crash
06 | 4 | Signage | Curzon Street (C4_PS01) | Signs overlapping each other. Need to be lifted.
07 | 4 | Signage | South Carriage Drive (C4_PS07) | Wrong sign diameter installed. Proposed Ø600mm and on site was installed Ø300mm