## Speed Related Work Orders
Works Order Number | Works Order Date Raised | Work Order Desciption | Date Instructed | WORKS ORDER CREATED / RAISED. | WORKS ORDER REPAIRED DATE/OR CLOSED OUT ON RINGWAYJACOBS SYSTEM. | Scope Of Works | Date Authorised
NE8_STO/104 | 2020-04-23 17:20 | A127/00.00 - Gallows Corner Flyover - Interim Measure (6 MONTHLY SPECIAL INSPECTION) | 2020-10-09 12:31 | 2020-05-05 16:24 | 2021-04-15 11:00 | GALLOWS CORNER FLYOVER – SPECIAL INSPECTION AND REVIEW OF BD79 RISK ASSESSMENT | 2020-10-09 12:31
NE8_HTO/171 | 2020-09-01 09:21 | A12/A127 GALLOWS CORNER FLYOVER - EMERGENCY 20MPH & 7.5T WEIGHT RESTRICTION SIGNAGE | 2020-09-02 15:39 | 2020-09-01 09:22 | 2021-04-15 11:00 | THE CONTRACTOR SHALL "DESIGN & IMPLEMENT" EMERGENCY "20MPH" & "7.5T WEIGHT RESTRICTION SIGNAGE, FOR BOTH APPROACHES TO THE GALLOWS CORNER FLYOVER. THE SIGNAGE SHOULD BE IN-SITU AT 00.01HRS ON FRIDAY 5TH SEPTEMBER, TO COINCIDE WITH THE 15:2 TRAFFIC ORDER. TASK ORDER FOR PERMANENT SIGNAGE TO FOLLOW. | 2020-09-02 15:39
NE8_HTO/172 | 2020-09-01 09:44 | A12/A127 GALLOWS CORNER FLYOVER - 20MPH & 7.5T WEIGHT RESTRICTION SIGNAGE | 2021-01-13 10:17 | 2020-09-01 09:45 | 2021-02-24 08:00 | FOLLOW ON TASK ORDER TO NE8_HTO/171. THE CONTRACTOR SHALL UNDERTAKE THE FOLLOWING. 1. "DESIGN & IMPLEMENT" APPROPRIATE 20MPH & 7.5T WEIGHT RESTRICTION SIGNAGE, TO REMAIN INSITU UNTI THE MAJOR PROJECT TAKES PLACE. 2. UNDERTAKE A FULL REVIEW OF SIGNAGE/ROAD MARKING AND CROSSING POINTS AS HIGHLIGHTED ON THE ATTACHED EMAIL. 3. UNDERTAKE A ROAD SAFETY AUDIT WITH THE POLICE | 2021-01-13 10:17
NE8_STO/308 | 2021-02-11 12:36 | A127/00.00 - Gallows Corner Flyover - Interim Measure (6 MONTHLY SPECIAL INSPECTION No.2) | 2021-02-23 12:22 | 2021-02-11 12:39 | 2021-04-15 11:00 | GALLOWS CORNER FLYOVER – SPECIAL INSPECTION NO.2 AND REVIEW OF BD79 RISK ASSESSMENT | 2021-02-23 12:22